## Spring Planning
AI- Powered System for Fruit Identification and Quality Assessment
Sprint No | Release No | Sprint Goal | Start Date | End Date | Daily Scrum | Meeting Room
1 | 1 | Research and select a fruit detection algorithm to identify various fruits. | 2024-06-17 | 2024-06-21
2 | 1 | Fruit Quality Assessment | 2024-06-24 | 2024-06-28
3 | 2 | User Interface | 2024-07-01 | 2024-07-05
4 | 2 | Scalability | 2024-07-08 | 2024-07-12
5 | 3 | Customer Support | 2024-07-15 | 2024-07-19
6 | 3 | Documentation | 2024-07-22 | 2024-07-26
Members | Availability | Comments
Christina | 100%
Ashwini | 100%
Dheeraj | 100%
Yokub | 100%
Prasanth | 100%
Sprint Demo
Date | Daily Scrum | Meeting Room
Note:
Please refer the next sheet for all tasks information

## AI-Powered system for Fruit Ded
Task | Priority | Owner | Status | Start date | End date | Milestone | Story Points | Deliverables | Notes
Develop Image Recognition Algorithm | P1 | carokiaswamy3489@conestogac.on.ca | Done | 6/17/2024 | 6/21/2024 | Release 1 | 5
User Authentication | P1 | agnanaseelanvim3858@conestogac.on.ca | Done | 6/17/2024 | 6/21/2024 | Release 1 | 5
Real-Time Identification | P1 | drawat9521@conestogac.on.ca | Done | 6/17/2024 | 6/21/2024 | Release 1 | 5
Database Integration | P1 | yyekini9553@conestogac.on.ca | Done | 6/17/2024 | 6/21/2024 | Release 1 | 5
Integrate Camera Functionality | P1 | pdhanapal7365@conestogac.on.ca | Done | 6/17/2024 | 6/21/2024 | Release 1 | 5
Visual Quality Assessment Algorithm | P2 | carokiaswamy3489@conestogac.on.ca | TODO | 6/24/2024 | 6/28/2024 | Release 1
Implement algorithms to identify the appropriate stage of ripeness of fruits | P2 | drawat9521@conestogac.on.ca | TODO | 6/24/2024 | 6/28/2024 | Release 1
Quality Score Display | P2 | pdhanapal7365@conestogac.on.ca | TODO | 6/24/2024 | 6/28/2024 | Release 1
Historical Data Tracking | P2 | agnanaseelanvim3858@conestogac.on.ca | TODO | 6/24/2024 | 6/28/2024 | Release 1
Identify models to identify exotic fruits | P2 | yyekini9553@conestogac.on.ca | TODO | 6/24/2024 | 6/28/2024 | Release 1
UI/UX Design | P3 | carokiaswamy3489@conestogac.on.ca | Done | 7/1/2024 | 7/5/2024 | Release 2
Mobile App Development | P3 | agnanaseelanvim3858@conestogac.on.ca | Done | 7/1/2024 | 7/5/2024 | Release 2
Web Interface Development | P3 | drawat9521@conestogac.on.ca | Done | 7/1/2024 | 7/5/2024 | Release 2
Localization | P3 | pdhanapal7365@conestogac.on.ca | Done | 7/1/2024 | 7/5/2024 | Release 2
Accessibility Features | P3 | yyekini9553@conestogac.on.ca | Done | 7/1/2024 | 7/5/2024 | Release 2
Online Shopping Integration | P4 | agnanaseelanvim3858@conestogac.on.ca | Done | 7/8/2024 | 7/12/2024 | Release 2
Nutritional Information Database | P4 | pdhanapal7365@conestogac.on.ca | Progress | 7/8/2024 | 7/12/2024 | Release 2
nventory Management Integration | P4 | drawat9521@conestogac.on.ca | Progress | 7/8/2024 | 7/12/2024 | Release 2
History about exotic fruits | P4 | carokiaswamy3489@conestogac.on.ca | Progress | 7/8/2024 | 7/12/2024 | Release 2
Social Media Sharing | P4 | yyekini9553@conestogac.on.ca | Progress | 7/8/2024 | 7/12/2024 | Release 2
In-App Tutorials | P5 | carokiaswamy3489@conestogac.on.ca | Progress | 7/15/2024 | 7/19/2024 | Release 3
Customer Support | P5 | agnanaseelanvim3858@conestogac.on.ca | Progress | 7/15/2024 | 7/19/2024 | Release 3
User Feedback and Surveys | P5 | pdhanapal7365@conestogac.on.ca | Progress | 7/15/2024 | 7/19/2024 | Release 3
Rewards and Gamification | P5 | drawat9521@conestogac.on.ca | Progress | 7/15/2024 | 7/19/2024 | Release 3
Community Building | P5 | yyekini9553@conestogac.on.ca | Progress | 7/15/2024 | 7/19/2024 | Release 3
User Manual | P5 | carokiaswamy3489@conestogac.on.ca | Progress | 7/22/2024 | 7/26/2024 | Release 3
API Documentation | P5 | agnanaseelanvim3858@conestogac.on.ca | Progress | 7/22/2024 | 7/26/2024 | Release 3
Technical Documentation | P5 | pdhanapal7365@conestogac.on.ca | Progress | 7/22/2024 | 7/26/2024 | Release 3
Training Materials | P5 | drawat9521@conestogac.on.ca | Progress | 7/22/2024 | 7/26/2024 | Release 3
Release Notes | P5 | yyekini9553@conestogac.on.ca | Progress | 7/22/2024 | 7/26/2024 | Release 3